## Summary
BIZBOARD — SaaS READINESS DASHBOARD
Use the Checklist sheet to update status, owner, due date and evidence. Summary metrics update automatically.
Status as of 2026-10-23 (deep-review fixes + ops pass recorded; 2026-10-24: 10 engineering items closed, BB-100 walk-through, second pass and F10 done; decisions D-01..D-20 in docs/roadmap/DECISIONS_2026-10-24.md, sign-off pack drafted for 15) from repo evidence. Nothing is proven on hosted staging yet; HO-n = people item n in docs/roadmap/SAAS_READINESS_HANDOVER_2026-10-22.md.
Metric | Value | Status | Count
Total checklist items |  | Not Started
Passed |  | In Progress
In Progress |  | Blocked
Blocked |  | Passed
Not Started |  | Accepted Risk
Accepted Risk
Completion %
Suggested launch gates
1. Stabilize core workflows: sales, purchase, inventory, GST and reconciliation.
2. Validate with real business users and capture acceptance evidence.
3. Prove tenant isolation, access controls and production security.
4. Test backup restoration, monitoring, incident response and rollback.
5. Launch to a limited cohort only after critical gates pass.

## SaaS Checklist
ID | Category | Checklist Item | Priority | Status | Owner | Target Date | Evidence / Test ID | Defect / Risk ID | Launch Blocker? | Notes
BB-001 | Product & Scope | Define target customers and Ideal Customer Profile (ICP) | High | In Progress | Product |  | docs/BUSINESS_ARCHETYPES_AND_PERSONAS.md; docs/roadmap/GROWTH_OS_DECISIONS_2026-09-30.md |  | No | ICP drafted (archetypes + 3 growth pilots); not signed by founder.
BB-002 | Product & Scope | Finalize supported business types and customer personas | High | In Progress | Product |  | docs/BUSINESS_ARCHETYPES_AND_PERSONAS.md; docs/FULL_SPECTRUM_PERSONA_VALIDATION_PLAN.md |  | No | Personas written; validation with real businesses not done.
BB-003 | Product & Scope | Freeze MVP scope and defer non-essential features | Critical | In Progress | Product |  | docs/FREEZE_SCOPE.md (D1-D5 resolved 2026-09-08); guard_freeze_table_b_defaults | SR0-01 | Yes | Sections A/B/C/G/H still need signature. Scope grew since (mfg, agents) and much of it is uncommitted on feat/mfg-p0-foundations.
BB-004 | Product & Scope | Document functional requirements and user workflows | High | In Progress | Product |  | docs/FREEZE_SCOPE.md; docs/requirements/; 51 journey cells; golden e2e as executable spec; docs/requirements/REQUIREMENTS_BASELINE.md |  | No | Spread across freeze scope, plans and tests; no single signed requirements doc.; 2026-10-24 A/B pass: Release-1 requirements baseline written (scope, additions since freeze, flags, limits, rules, NFRs). Awaiting founder signature.; 2026-10-25: baseline already consolidated in docs/requirements/REQUIREMENTS_BASELINE.md (sign-off pack B-14); awaiting founder signature only.
BB-005 | Product & Scope | Finalize pricing plans, trial period and feature limits | High | In Progress | Business |  | billing module: plans, trial, quotas, entitlements; docs/roadmap/SIGNOFF_PACK_2026-10-23.md B-1, B-2 | HO-18; SR3-01 | No | Mechanism built. Prices, trial length and limits not signed by founder.; 2026-10-24 A/B pass: Plans/prices (₹0/499/1,499/4,999) and 14-day trial proposed from the seeded values. Awaiting founder signature (CA for SaaS GST).; 2026-10-25: found - seeded paid plans switch the GSTR-1/3B worksheets off (ENABLE_GSTR in FREEZE_DARK_PLAN_MODULES) while the trial has them, so an upgrading customer would lose them. Awaiting founder decision on which paid plans include them.; 2026-10-25 (D-16): GST worksheets (GSTR-1/3B) granted on all four plans, like the trial (freeze_safe_modules + migration billing 0021). Prices still unsigned.
BB-006 | Product & Scope | Document known issues and limitations | Medium | Passed | Product |  | docs/help/LIMITATIONS.md; in-app /help/pilot-limits and public /limits (en+hi); guard_limitations_page; PilotLimitsPage.test.tsx |  | No | Kept in step with flags by CI guard.
BB-007 | Core Business Functionality | Validate sales workflow: orders, invoices, payments, returns and credit notes | Critical | In Progress | QA |  | Golden e2e live on Postgres 17 (130 pass, 2 fixed); sales invoice, returns (SRF), credit/debit note suites; test_customer_lock_deadlock_postgres.py | QOS-0097 | Yes | Real bugs fixed (deadlock, freight tax, zero-value invoice). Needs run by a real operator on hosted staging and CA sign-off.
BB-008 | Core Business Functionality | Validate purchase workflow: purchase invoices, GRN, payments and debit notes | Critical | In Progress | QA |  | Purchase review fixes (commits c1169a8, f5523be); purchase returns/pay-now Postgres concurrency suites; golden e2e |  | Yes | 2026-10-24: browser check done (purchase bill with a new supplier on local staging: totals, payable and stock correct; BB100_JOURNEY_WALKTHROUGH_2026-10-24.md); purchase orders now take the HSN-table GST rate like bills. Left: CA sign-off, hosted run, PB-01 (CA question), PB-02/PB-03 already fixed (searchable supplier filter on planning, paged server-searched supplier list).
BB-009 | Core Business Functionality | Validate inventory ledger and stock balance accuracy | Critical | In Progress | QA |  | Inventory review WP-00..21 + deep review IDR-01..14 (Postgres races pass); invariant sweep | QOS-0072; HO-8 | Yes | Stock value vs inventory account is not an invariant (periodic valuation by design). Stock GL postings flag off until CA signs.
BB-010 | Core Business Functionality | Validate multi-godown stock transfers and reconciliation | Critical | In Progress | QA |  | Inventory review suites (transfers, godowns); test_inventory_idr14_concurrency_postgres.py |  | Yes | Proven in repo only; no real multi-godown business yet.
BB-011 | Core Business Functionality | Validate batch, serial number and FIFO costing where supported | High | Passed | QA |  | docs/requirements/ITEM_STOCK_GODOWN_EXPIRY.md; inventory suites; 115 batch/serial/expiry/FEFO tests pass (test_inventory_serials_wp02.py, test_wave15_fefo.py, test_inventory_idr06_expiry.py and 9 more) |  | No | Batch/expiry supported. FIFO not supported: stock cost is weighted average (documented on /limits, key 'cost').; 2026-10-24 A/B pass: Batch, serial and expiry verified; FIFO layers are a documented limitation (weighted average, /limits "cost").
BB-012 | Core Business Functionality | Validate customer and supplier master data | High | In Progress | QA |  | CRM review WP-1..8; test_customers_concurrency_postgres.py; GSTIN tests |  | No | Needs real customer master import (SR2-01).
BB-013 | Core Business Functionality | Verify receivables, payables and outstanding balances | Critical | In Progress | QA |  | tests/test_gl_parity_invariants.py (AR/AP tie to documents incl. opening balances); Money In phase 2; Money Hub | QOS-0129 | Yes | CA sign-off open.
BB-014 | Core Business Functionality | Validate financial reports and dashboards against source transactions | Critical | In Progress | QA |  | Accounting screens ACS-00..73; invariant sweep; Insights INP-00..24; dashboard attention DAN-00..19 | QOS-0130..0133; QOS-0137..0139 | Yes | CA, Hindi and device sign-offs open.
BB-015 | Core Business Functionality | Validate document numbering, cancellation and audit history | Critical | In Progress | QA |  | core/services/sequences.py (gap-free numbering); audit hash chain; DB trigger on posted entries (test_ledger_trigger_postgres.py) |  | Yes | Proven in repo/Postgres; not on hosted staging.
BB-016 | Core Business Functionality | Validate data import, export and migration | High | In Progress | QA |  | Tally CSV/XLSX/XML import (test_tally_xml_import.py); Busy/Vyapar/Marg (test_legacy_import_gr1b.py); readable export (test_readable_export_dl1.py); cutover_recon; test_saas_review_fixes.py (import cases) | HO-15; SR2-01 | No | No real customer files imported yet; column maps unconfirmed against pilot files.; 2026-10-23 review: Import fixes: Tally XML sub-groups and IGST rate, strict balance parsing, advances listed not dropped, stable item codes, file row numbers in errors.
BB-017 | Core Business Functionality | Run end-to-end regression testing across modules | Critical | In Progress | QA |  | Golden e2e suite (CI merge gate) run live; strict-invariant lane green except laptop timing budgets; Postgres lane 119 pass / 0 skip | SR0-01 | Yes | Large part of the tree not yet through CI; not run on hosted staging.; 2026-10-25 (WP, LLM plan): All blocking CI gates run locally (D-20: no commit): ruff, web lint/tsc, migrations check, help codes, register claims, guards, OpenAPI/types regenerated, web build + SW + bundle budget, npm audit/pip-audit clean, 406 web test files pass, backend on Postgres 6975 passed; the 52 that failed under 4-worker load re-run serially: 173/175 pass, the 2 left are timing limits only (Complete 2.7 s vs 2.5 s; 5,000-product index) while another session's mutation run used ~4 CPU cores - CI decides, diff coverage 92%. Left: commit go-ahead and green CI.
BB-018 | GST & Regulatory Compliance | Validate GSTIN and business registration fields | High | Passed | Compliance |  | test_sprint3_series_gstin.py; test_series_gstin_health.py; test_w0_multi_gstin_complete.py; test_b06_020_cross_tenant_membership_gstin.py |  | No
BB-019 | GST & Regulatory Compliance | Validate HSN/SAC and applicable tax rates | Critical | In Progress | Compliance |  | masters HsnRate with valid_from/valid_to; test_b06_hsn_rate.py; test_hsn_catalog_reseed.py | QOS-0004 | Yes | Rate catalogue needs CA review.
BB-020 | GST & Regulatory Compliance | Test CGST, SGST, IGST and place-of-supply scenarios | Critical | In Progress | Compliance |  | Tax parity corpus F1-F8; core/services/place_of_supply.py | QOS-0004 | Yes | Automated in repo; no CA sign-off yet.
BB-021 | GST & Regulatory Compliance | Validate GST invoices and credit/debit notes | Critical | In Progress | Compliance |  | Credit/debit notes rev-2 plan built; test_sprint2_cn_einvoice.py; test_credit_debit_notes_concurrency_postgres.py | QOS-0004 | Yes | CA sign-off open.
BB-022 | GST & Regulatory Compliance | Validate GST reports and reconciliation outputs | Critical | In Progress | Compliance |  | GSTR-1/3B worksheets snapshot-pinned; test_sprint2_gstr_notes.py; test_reports_rpt07_itc_4b.py | QOS-0004 | Yes | No CA has filed from these worksheets yet.; 2026-10-24: bills of supply missing from GSTR-1 Table 8/13 and GSTR-3B 3.1(c)/(e) - options note for the CA in docs/ca/F2_BILLS_OF_SUPPLY_IN_GST_RETURNS.md (D-09: no code change until the CA decides).; 2026-10-25 (D-14): bills-of-supply treatment (options B+A) built behind GST_BILL_OF_SUPPLY_RETURNS, off for every company until the CA agrees; test_bill_of_supply_returns.py.
BB-023 | GST & Regulatory Compliance | Test GST portal integration and credential management | High | Accepted Risk | Integration |  | FREEZE_SCOPE C1; GSP_LIVE_ENABLED off; /limits key 'filing' |  | No | Not in this release: worksheets for the CA, who files on the portal.
BB-024 | GST & Regulatory Compliance | Document e-invoice/IRN and e-way bill scope and eligibility | High | Passed | Compliance |  | FREEZE_SCOPE C2; /limits key 'einvoice'; test_einvoice_eway.py |  | No | Scope documented: preview only, no live IRN/e-way bill; customers above threshold keep their current tool.
BB-025 | GST & Regulatory Compliance | Validate IMS and GSTR-2B workflows and ITC deadline calculations | High | Accepted Risk | Compliance |  | /limits key 'itcMatch'; test_b03_ims.py; test_itc_digest_and_lead_reminders.py |  | No | 2B/IMS matching not in this release (C1). ITC expiry digests exist.
BB-026 | GST & Regulatory Compliance | Review statutory requirements with a qualified GST professional | Critical | Blocked | Compliance |  | docs/ca/SAAS_CA_PACK.md (review pack ready) | HO-7; QOS-0004/0129/0130/0136/0138/0141 | Yes | CA not yet engaged.; 2026-10-24: CA_SIGN_OFF_CHECKLIST.md row R1 added (bills of supply).
BB-027 | SaaS Architecture & Multi-Tenancy | Verify distinct tenant/company identity for every business | Critical | Passed | Architecture |  | CompanyScopedModel on every tenant table; RLS coverage test; guard_module_readiness (27 apps) |  | Yes
BB-028 | SaaS Architecture & Multi-Tenancy | Ensure database queries enforce tenant boundaries | Critical | In Progress | Security |  | Postgres RLS with NOSUPERUSER NOBYPASSRLS app role; postgres-rls CI job; guard_compose_rls; local staging enforced | SR1-02 | Yes | Proven locally only; needs the tenancy + RLS suites against a hosted DB.; 2026-10-24: Postgres-only suites (row-level security, concurrency, tenancy) re-run on a fresh local Postgres: 543 passed, 1 skipped. Still to run on the hosted database.
BB-029 | SaaS Architecture & Multi-Tenancy | Test cross-tenant access via APIs, reports and exports | Critical | In Progress | Security |  | tests/tenancy/test_endpoint_isolation.py (route matrix); test_preauth_writes_rls_postgres.py | HO-10 | Yes | Hosted-staging run and independent pentest pending.; 2026-10-25 (WP, LLM plan): Live cross-tenant probe through nginx with RLS on (scripts/security/tenant_probe.py): 0 leaks on reads and list filters; writes naming the other company refused (400). Sales-staff logins only; owner roles left to the pentest and the Postgres tenancy suites.
BB-030 | SaaS Architecture & Multi-Tenancy | Test tenant isolation for caches, files and background jobs | Critical | In Progress | Security |  | test_beat_tasks_rls_postgres.py (8 beat tasks fixed); guard_no_inline_company_loops; per-company sweep; test_saas_review_fixes_postgres.py | SR1-02 | Yes | Proven in repo; hosted run pending.; 2026-10-23 review: Fixed: rls_bypass() did not nest, so staff admin lists (TDS claims, ownership transfers) were empty on Postgres; shared bypass admin mixin.; 2026-10-24: Postgres-only suites (row-level security, concurrency, tenancy) re-run on a fresh local Postgres: 543 passed, 1 skipped. Still to run on the hosted database.
BB-031 | SaaS Architecture & Multi-Tenancy | Support multiple users within one company | High | Passed | Identity |  | CompanyUser roles; test_wave4_rbac.py; test_sprint0_rbac_books.py |  | No
BB-032 | SaaS Architecture & Multi-Tenancy | Test secure company switching without data leakage | Critical | In Progress | Security |  | tests/tenancy/test_company_switch.py; web companyContext.test.ts, noDirectApiLinks.test.ts; X-Company-Id required for multi-company users; companyContext.test.ts (clear-then-set case) |  | Yes | Mobile (Capacitor) outbox case not proven on device.; 2026-10-23 review: Fixed: active company stored at sign-in (multi-company first requests had no X-Company-Id); other tabs reload when the company is cleared too.
BB-033 | SaaS Architecture & Multi-Tenancy | Define tenant creation, suspension and deletion workflows | High | Passed | Architecture |  | docs/ops/TENANT_MODEL.md; test_billing_suspend.py; test_erasure.py; docs/ops/ERASURE_PLAYBOOK.md; test_saas_review_fixes.py |  | No | 2026-10-23 review: Fixed: PROTECT links (support grant -> ticket, TDS claim -> certificate) blocked company erasure and restore; erasure now also deletes readable-export ZIPs.
BB-034 | SaaS Architecture & Multi-Tenancy | Define tenant data export and retention policies | High | In Progress | Privacy |  | DL1 readable export; tenant export; core/services/retention.py; docs/ops/DATA_CATEGORIES.md; LOG_RETENTION.md | HO-9 | No | Retention policy needs counsel sign-off.; 2026-10-23 review: Export no longer stuck PENDING forever; streamed to disk; all 12 pinned sections now really pinned in the column snapshot.; 2026-10-25: retention period now configurable per company (D-13); see BB-070.
BB-035 | User Management & Access Control | Validate user registration and company onboarding | High | In Progress | Identity |  | Sign-up with bot check (AB2), one trial per business (AB3), legal acceptance, onboarding checklist (GR2); test_google_signin_id5.py | HO-6; SR2-02 | No | Turnstile keys pending; unaided onboarding with real users not done.; 2026-10-23 review: Google sign-up now uses the password sign-up rules (state required etc.); bot-check widget reset loop fixed.
BB-036 | User Management & Access Control | Validate login, logout and password reset | Critical | In Progress | Identity |  | test_mfa.py; lockout and throttles; post_deploy_smoke.py --live-comms | HO-6 | Yes | Code tested. Phone OTP and reset email cannot reach real users until DLT and SPF/DKIM are done.
BB-037 | User Management & Access Control | Implement email/mobile verification where required | Medium | Blocked | Identity |  | OTP flows; SMS DLT template registry (test_message_templates.py) | HO-6 | No | Waiting on TRAI DLT entity/templates and SPF/DKIM/DMARC.
BB-038 | User Management & Access Control | Verify role-based access control | Critical | Passed | Security |  | test_wave4_rbac.py; test_mfg_role_matrix.py; test_inventory_idr12_roles.py; test_next_batch_roles.py |  | Yes | Pentest will re-check (HO-10).
BB-039 | User Management & Access Control | Test staff invitations and account deactivation | High | Passed | Identity |  | InviteJti invites; last-owner protection (ID1); tests/test_saas_phase1_ops.py |  | No
BB-040 | User Management & Access Control | Validate session expiry and secure authentication | Critical | Passed | Security |  | httpOnly JWT cookies, 15-min access token, refresh blacklist; MFA on every sign-in path (QOS-0103 closed); sessions screen (test_user_sessions_id3.py); test_user_sessions_id3.py (switch-company, logout cases) |  | Yes | 2026-10-23 review: Fixed a hole: /auth/switch-company/ issued a new 14-day session from an access token, undoing 'sign out this device'. Logout/reset now close sessions; Security page for every user.
BB-041 | User Management & Access Control | Protect sensitive financial and administrative actions | Critical | Passed | Security |  | Password + MFA re-check on sensitive actions; ownership transfer; break-glass (tests/test_saas_phase1_ops.py); test_saas_review_fixes.py (ownership cases) |  | Yes | 2026-10-23 review: Fixed: an ownership offer stayed valid after its owner was demoted; Google sign-in could open an account by email on non-Google mail domains.
BB-042 | User Management & Access Control | Audit important user activities | High | Passed | Security |  | AuditService + audit hash chain; test_plan_audit_seal_session.py; repair trail (test_repair_trail.py) |  | No | Owner-facing audit log screen deferred to after launch (I-04).
BB-043 | Security & Privacy | Enforce HTTPS | Critical | Blocked | Security |  | Production settings: secure cookies, HSTS; SECURE_SSL_REDIRECT opt-in; edge_tls_smoke.sh | HO-2; HO-3 | Yes | No hosted environment yet to verify TLS end to end.
BB-044 | Security & Privacy | Keep API keys and secrets outside source control | Critical | Passed | Security |  | Settings from env; .env.*.example only; boot refuses without required keys; key rotation (test_key_rotation.py) | SR1-10 | Yes | Secrets manager on the host still to set up.
BB-045 | Security & Privacy | Test SQL injection, XSS, CSRF and authorization vulnerabilities | Critical | In Progress | Security |  | CSRF on, ORM only, CodeQL workflow, STRIDE.md, test_payment_webhook_adversarial.py | HO-10 | Yes | Independent pentest on hosted staging not done.; 2026-10-23 ops pass: Two security fixes this pass: spoofable client IP in rate limits; permanent-lockout counter race (see BB-046). Pentest still pending.; 2026-10-25 (WP, LLM plan): Local ZAP baseline + signed-in API scan (7 batches) + cross-tenant probe: 0 injection, 0 cross-tenant read/write; ZAP SQLi alerts proven false positives (rate-limit 503s); fixed missing Permissions-Policy/COOP/CORP headers and HTML 404s on /api/ (docs/security/LOCAL_SCAN_2026-10-25.md). Pentest brief ready (docs/security/PENTEST_SCOPE.md). Left: independent pentest on hosted staging.
BB-046 | Security & Privacy | Apply rate limiting and abuse protection | High | In Progress | Security |  | DRF throttles (otp, sensitive_action, public_link); SMS guard (test_sms_guard.py); bot check (test_bot_check.py); test_public_pay_rate_limit.py; test_saas_review_fixes.py (SMS, Turnstile); NUM_PROXIES = NUM_TRUSTED_PROXIES (test_throttle_client_ip.py); core/services/counters.py TTL fix (test_cache_counters_ttl.py) | HO-2 | No | Turnstile keys not set; no WAF/DDoS layer yet.; 2026-10-23 review: Fixed: dunning SMS shared the OTP number-series budget; Turnstile and public-link spread used the proxy address; Turnstile hostname check added.; 2026-10-23 ops pass: Fixed: anonymous throttles keyed on a client-controlled X-Forwarded-For (a new value per request bypassed every limit); a Redis counter race could leave a rate-limit or lockout key with no expiry, locking a user out of the API until Redis was flushed (seen live on staging).
BB-047 | Security & Privacy | Protect customer financial and personal data | Critical | In Progress | Security |  | RLS; MFA; encrypted secrets at rest; PII kept from AI models (tests/agents); public-link hardening (test_public_link_hardening.py) | HO-9; HO-10 | Yes | Counsel/DPIA and pentest pending.; 2026-10-25 (WP, LLM plan): Covered by the DPIA draft (risks R1-R13 with controls); stale RLS/MFA facts corrected in STRIDE.md and PRODUCT_BEHAVIORS_FOR_COUNSEL.md. Left: counsel + pentest.
BB-048 | Security & Privacy | Prevent sensitive information from appearing in logs | Critical | Passed | Security |  | Sentry with request_id + company_hash (no raw tenant ids); agent PII tests; core/log_redaction.py (RedactingFormatter on every console handler); tests/test_log_redaction.py (21 tests incl. repo-wide AST scan) |  | Yes | No repo-wide log redaction test; check on hosted logs.; 2026-10-24 A/B pass: Repo-wide scan found no logging call passing a password/token/OTP/key; redaction of secrets, JWTs, emails, phones, PAN, Aadhaar, cards added as a safety net, tracebacks included.
BB-049 | Security & Privacy | Configure dependency and vulnerability scanning | High | Passed | Security |  | .github/dependabot.yml (pip, web, mobile); pip-audit; npm audit; CodeQL; supply-chain CI job (Trivy + CycloneDX SBOM) |  | No | 2026-10-23 review: Fixed: supply-chain job lacked PyYAML (would fail every run); backend SBOM had no packages (now from a resolved env); docker scan now honours the allow-list.
BB-050 | Security & Privacy | Publish privacy policy and terms of service | High | Blocked | Legal |  | Acceptance recording + re-accept flow built (test_legal_acceptance.py) | HO-9 | No | Counsel to write ToS and privacy policy.; 2026-10-24 (D-07): first drafts for counsel in docs/legal/drafts/ (terms, privacy policy, DPA), with sub-processors and open points listed. Counsel must rewrite and approve.
BB-051 | Security & Privacy | Establish incident response and data breach procedures | High | In Progress | Security |  | docs/ops/INCIDENT_RESPONSE.md (CERT-In 6-hour clock); DPDP_REQUESTS.md breach fields; POSTMORTEM.md; docs/ops/TABLETOP_EXERCISES.md; ONCALL_ROSTER.md filled | HO-5; SR2-10 | No | No named on-call; tabletop not held; counsel wording pending.; 2026-10-23 ops pass: On-call primary named (founder); no backup yet (recorded as a risk). Tabletop pack ready; not held.; 2026-10-25 (WP, LLM plan): Incident tabletop run pack (inject cards, scoring sheet, solo record) added to TABLETOP_EXERCISES.md. Left: founder runs it; backup on call.
BB-052 | Subscription & Payments | Define subscription plans and pricing | High | In Progress | Business |  | Plans defined in billing module; docs/roadmap/SIGNOFF_PACK_2026-10-23.md B-1 | HO-18 | No | Prices not signed.; 2026-10-24 A/B pass: Plan and price proposal drafted. Awaiting founder signature.; 2026-10-25: found - seeded paid plans switch the GSTR-1/3B worksheets off (ENABLE_GSTR in FREEZE_DARK_PLAN_MODULES) while the trial has them, so an upgrading customer would lose them. Awaiting founder decision on which paid plans include them.; 2026-10-25 (D-16): every plan, Free included, now grants the GSTR-1/3B worksheets; pricing page shows it.
BB-053 | Subscription & Payments | Implement free trial and trial expiry | High | Passed | Payments |  | ensure_register_trial; trial expiry write-block; one trial per business (test_tds_claims_trial_guard.py) | HO-18 | No | Trial length still to be signed.
BB-054 | Subscription & Payments | Integrate payment gateway and test production readiness | Critical | Blocked | Payments |  | Razorpay integration (sandbox); 152 billing/gateway tests pass (mocked gateway) | HO-18; QOS-0031 | Yes | Live Razorpay account, keys and live daily recon pending.; 2026-10-23 ops pass: Sandbox runs skipped: no Razorpay test keys yet.
BB-055 | Subscription & Payments | Handle payment success, failure, refunds and renewals | Critical | In Progress | Payments |  | Webhooks, dunning, BL2 invoice per renewal, BL1 refunds, BL3 proration, BL4 UPI Autopay (test_plan_change_autopay.py); test_plan_change_autopay.py (review-fix tests) |  | Yes | Razorpay sandbox runs of upgrade/downgrade/re-mandate/renewal pending.; 2026-10-23 review: Fixed money bugs: double charge at renewal on a plan switch, repeat-upgrade re-charge, paid upgrade never expiring, pending plan promoted by the old renewal, paid links dropped.
BB-056 | Subscription & Payments | Validate webhook signatures and duplicate event handling | Critical | Passed | Payments |  | HMAC verification; ProcessedWebhookEvent + event-id/payment-id dedupe; test_payment_webhook_adversarial.py; test_w0_webhook_holding.py |  | Yes | Signed replay on staging still to do.; 2026-10-23 review: Unknown subscription events are now parked before being applied (no status change from them).
BB-057 | Subscription & Payments | Implement subscription invoices and payment history | High | In Progress | Finance |  | PlatformGstInvoice for every charge incl. Razorpay renewals, PDFs, owner list (test_platform_gst_bl2.py) | HO-18 | No | CA to sign invoice format and SAC.; 2026-10-23 review: Fixed: recon would have invoiced every historical charge dated today (now 35-day window + PLATFORM_GST_INVOICES_FROM); CGST/SGST equal halves by GST state code.
BB-058 | Subscription & Payments | Enforce plan-based feature and usage limits on the backend | Critical | Passed | Engineering |  | billing/quotas.py; entitlements; write-block; test_saas_quotas_and_dlq.py |  | Yes | 2026-10-23 review: Upgrade seat limit now applies to invites at once.
BB-059 | Subscription & Payments | Define grace periods for failed payments | High | In Progress | Business |  | SaaS dunning (PAST_DUE); 3-day grace on unpaid proration; docs/roadmap/SIGNOFF_PACK_2026-10-23.md B-3 |  | No | Grace-period policy not signed by founder.; 2026-10-24 A/B pass: Proposal: 7-day grace (today 0) then read-only, data kept. Awaiting founder signature.
BB-060 | Subscription & Payments | Implement subscription cancellation and reactivation | High | In Progress | Payments |  | Billing danger zone (cancel); mandate cancel/resume (BL4) |  | No | Sandbox run pending.
BB-061 | Subscription & Payments | Preserve customer data during suspension and downgrade | Critical | Passed | Engineering |  | Suspension is read-only, never deletion; downgrade refused over quota; test_billing_suspend.py |  | Yes
BB-062 | Database & Data Integrity | Review database schema and relationships | High | Passed | Engineering |  | Per-module reviews (sales, purchase, inventory, accounting, CRM, mfg); schema constraints; docs/architecture/SCHEMA_REVIEW_2026-10-23.md; payments migration 0046 (unique receipt/payment numbers) |  | No | No single signed schema review.; 2026-10-24 A/B pass: 274 models reviewed: tenancy + RLS coverage, no float money, delete rules safe, indexes present. Fixed: receipts and supplier payments now have a DB-level unique number per company.
BB-063 | Database & Data Integrity | Validate transaction integrity for financial postings | Critical | Passed | Engineering |  | Deferred DB triggers reject unbalanced/empty posted entries (test_ledger_trigger_postgres.py); test_a2_posting_atomicity.py; property-based ledger test + nightly-ledger.yml |  | Yes
BB-064 | Database & Data Integrity | Test concurrent invoice creation and stock updates | Critical | Passed | Engineering |  | 15+ *_concurrency_postgres.py suites; test_customer_lock_deadlock_postgres.py; check_postgres_skips.py (no skips in CI) |  | Yes
BB-065 | Database & Data Integrity | Reconcile inventory ledger with stock balances | Critical | In Progress | Engineering |  | Invariant sweep per tenant (test_tenant_sweep.py); restore drill sweep clean | QOS-0072; HO-8 | Yes | Stock value vs inventory account not an invariant by design; stock GL postings off until CA signs.
BB-066 | Database & Data Integrity | Validate database migrations | Critical | Passed | Engineering |  | migration-ledger-gate CI job (required); test_zdt_migrations.py; migration-rehearsal.yml | QOS-0014 | Yes | Rehearsal on a copy of real data needs a production dump.
BB-067 | Database & Data Integrity | Add required indexes and review slow queries | High | Passed | Engineering |  | docs/ops/INDEXES.md; test_phase0_api_slas.py; test_ws08_report_performance.py; core/services/lookup_cache.py; tests/test_complete_query_budget.py; docs/architecture/SCHEMA_REVIEW_2026-10-23.md (indexes) | QOS-0003 | No | Shadow books add ~50 queries to invoice Complete; reduction tracked.; 2026-10-24 A/B pass: Complete with ledger on: 151 -> 146 queries (ledger overhead 49 -> 44, budget-guarded). Remaining are period locks, numbering and journal writes by design; all hot lookups indexed. 1,124 money-path tests pass.
BB-068 | Database & Data Integrity | Configure connection pooling and transaction handling | High | In Progress | Engineering |  | pgbouncer session mode (guarded); DB_CONN_MAX_AGE; docs/ops/POSTGRES.md |  | No | Transaction pooling deliberately not built. Not on a host yet.; 2026-10-25 (WP, LLM plan): PgBouncer overlay built and tested locally (docker-compose.pgbouncer.yml, session mode, auth_query, no password on disk); role-level 30s/60s timeouts fixed a silent loss through the pool; boot guard; CI render check. Measured slower than direct on the laptop, so production starts without it (docs/ops/POSTGRES.md). Left: decide/confirm on the host.
BB-069 | Database & Data Integrity | Test large datasets and historical records | High | In Progress | Performance |  | seed_load_tenant; load/SEED_50K.md; dashboard p95 spec (2.8-6.0 s on laptop); seed_load_tenant staff login; seed_draft_pool top-up | QOS-0003 | No | Large-tenant run on hosted infra pending.; 2026-10-23 ops pass: Load tenant now has a sales-staff login outside the two-step rule; seed_draft_pool no longer fails on a tenant with opening stock.
BB-070 | Database & Data Integrity | Establish data retention and deletion procedures | High | In Progress | Privacy |  | core/services/retention.py; ERASURE_PLAYBOOK.md; DPDP request register | HO-9 | No | Counsel sign-off pending.; 2026-10-25 (D-13): owner-set retention for read-only workspaces (default 90 days, 30-3650), warnings 30 and 7 days ahead, tombstone erasure behind DATA_RETENTION_ENFORCE (off until counsel confirms); docs/ops/DATA_RETENTION.md, test_data_retention.py.
BB-071 | Performance & Scalability | Define performance SLAs for critical workflows | High | In Progress | Performance |  | docs/ops/SLO.md (draft); docs/roadmap/SIGNOFF_PACK_2026-10-23.md B-6; docs/ops/SLO.md | HO-19 | No | Not signed.; 2026-10-24 A/B pass: Proposal: sign SLO.md targets as is; keep Complete cap 30/min/company. Awaiting founder signature.; 2026-10-25 (D-11): Complete cap decided - 60 per minute per company (was 30); purchase bills stay at 30. SLO table itself still awaits signature.
BB-072 | Performance & Scalability | Test concurrent users | High | Blocked | Performance |  | load/k6_mixed.js, k6_slo.js, locust_smoke.py; k6 v1.8.1 installed; dry run on local staging (load/README.md) | HO-11; QOS-0003 | No | Needs hosted staging.; 2026-10-23 ops pass: Scripts proven locally. Fixed: k6_slo/k6_mixed "passed" with zero work (bearer token staging never sends). Before the hosted run decide: sales_complete cap 30/min per company; one staff login per VU.; 2026-10-24: month_end.js answers the owner two-step challenge (TOTP_SECRETS); dry run on local staging passed. Left: the hosted run.; 2026-10-24 (D-10): seed_load_tenant --staff 25 and k6_mixed.js STAFF_EMAILS give each VU its own login; dry run on local staging 357 requests, 0 failed.; 2026-10-25: k6_slo.js also uses one login per VU and runs Completes at COMPLETES_PER_MIN (default 50, under the 60/min cap); k6_mixed.js writers paced the same. Local dry run: 353 requests, 0 failed, no 429s (Completes were 26% 2xx before). Hosted run still needed.
BB-073 | Performance & Scalability | Test invoice creation, search, reports and dashboards | High | In Progress | Performance |  | test_phase0_api_slas.py; test_acs_performance_budgets.py; v95-dashboard-p95.spec.ts | QOS-0003; QOS-0016 | No | Measured on laptop only.
BB-074 | Performance & Scalability | Test large imports and exports | High | In Progress | Performance |  | Import wall-clock test | QOS-0003 | No | 2026-10-24: import commit loads only the SKUs in the file; 5,000-row catalogue upload + commit 8.7-8.9 s on Postgres, I4 gate passes on Postgres and SQLite (laptop). Left: confirm on the hosted server.; 2026-10-25: looked for more speed; the rest is Django preparing ~225,000 insert values, and bypassing the ORM is not worth the risk. Stays at 8.7-8.9 s against 10 s; confirm on the hosted server.
BB-075 | Performance & Scalability | Identify CPU, memory and database bottlenecks | Medium | Blocked | Performance |  | Prometheus metrics (multiprocess), deploy/prometheus/ | HO-11 | No | Needs load on hosted infra.; 2026-10-23 ops pass: No change: needs load on hosted infra.
BB-076 | Performance & Scalability | Optimize slow queries and expensive API calls | High | In Progress | Engineering |  | Performance budget tests | QOS-0003 | No | Waits on hosted load results.; 2026-10-25 (WP, LLM plan): Initial web load cut from 721.7 KB to 496.6 KB gzip (Hindi catalogue and page-help catalogue now load on demand); bundle budget 530 KB passes again. Left: hosted load results.
BB-077 | Performance & Scalability | Configure background jobs, retries and timeouts | High | Passed | Engineering |  | Separate Celery queues; retries + DLQ/replay; per-company fan-out with crash isolation; guard_no_inline_company_loops |  | No
BB-078 | Performance & Scalability | Test application behavior under load | High | Blocked | Performance |  | load/ scripts; load/month_end.js; k6 smoke on local staging: 289 requests, 0 failed | HO-11 | No | Load and 8-hour soak need hosted staging; k6 not installed locally.; 2026-10-23 review: month_end.js fixed: could not sign in on staging (cookie-only); arrivals now spread over the window.; 2026-10-23 ops pass: k6 is now installed locally (the note above is stale). month_end.js owners need a two-step (TOTP) step before it can run on staging; SOAK_MINUTES added for short dry runs.; 2026-10-24: month_end.js answers the owner two-step challenge (TOTP_SECRETS); dry run on local staging passed. Left: the hosted run.; 2026-10-24 (D-10): seed_load_tenant --staff 25 and k6_mixed.js STAFF_EMAILS give each VU its own login; dry run on local staging 357 requests, 0 failed.; 2026-10-25: k6_slo.js also uses one login per VU and runs Completes at COMPLETES_PER_MIN (default 50, under the 60/min cap); k6_mixed.js writers paced the same. Local dry run: 353 requests, 0 failed, no 429s (Completes were 26% 2xx before). Hosted run still needed.
BB-079 | Performance & Scalability | Define capacity monitoring and scaling thresholds | Medium | In Progress | Operations |  | docs/ops/WORKER_SCALE.md; queue-depth metrics and alerts; docs/roadmap/SIGNOFF_PACK_2026-10-23.md B-7 | HO-19 | No | Capacity numbers not signed.; 2026-10-24 A/B pass: Scale thresholds proposed (CPU, memory, DB connections, disk, Celery backlog, p95). Awaiting founder signature.
BB-080 | Deployment & DevOps | Separate development, staging and production environments | Critical | Blocked | DevOps |  | Local dev + local staging (port 8081) + prod compose overlay | HO-2; HO-3 | Yes | Hosted staging and production not provisioned.; 2026-10-25 (WP, LLM plan): Provider-neutral hosting kit (D-18): scripts/host/bootstrap_vm.sh (--check), render_env.sh (secret store -> .env, refuses placeholders), preflight.py (PASS/FAIL incl. RLS role, timeouts, TLS, HSTS, ports open around ufw, backups, OPS_ALERT_TOKEN); first-boot checklist in HOSTED_STAGING.md. Left: pick provider and run it.
BB-081 | Deployment & DevOps | Configure production environment variables and secrets | Critical | In Progress | DevOps |  | .env.production.example; production boot refusals (RLS, MFA key, Turnstile); web/Dockerfile, cd.yml | HO-2; SR1-10 | Yes | Real values and secrets manager need the host.; 2026-10-23 review: Fixed a launch blocker: VITE_TURNSTILE_SITE_KEY / VITE_GOOGLE_CLIENT_ID never reached the built web bundle (production would refuse every sign-up/OTP/reset). Set them as CD repository variables. New: EMAIL_WEBHOOK_USER/PASSWORD (were never defined, bounce webhook refused everything), PLATFORM_GST_INVOICES_FROM, TURNSTILE_ALLOWED_HOSTNAMES.; 2026-10-25 (WP, LLM plan): render_env.sh builds .env from AWS SSM / Azure KV / GCP SM / any command and refuses placeholder values; preflight checks required values. Left: real secrets on the host.
BB-082 | Deployment & DevOps | Automate deployment using CI/CD | High | In Progress | DevOps |  | ci.yml, cd.yml, deploy-staging.yml (deploy from SHA + rollback) | HO-3 | No | No hosted target yet.; 2026-10-25 (WP, LLM plan): deploy-staging.yml already reads host/user/dir from the staging environment secrets; documented which secrets to create and a required reviewer. Left: a host to deploy to.
BB-083 | Deployment & DevOps | Run automated tests before deployment | Critical | Passed | DevOps |  | Required CI jobs: backend, golden e2e merge gate, postgres-rls, migration-ledger-gate, supply-chain, guards | SR0-01 | Yes | Uncommitted work has not been through CI yet.; 2026-10-23 review: Guards hardened (aliased mail imports, private SMS senders, all Trivy allow-list sections); merge-size reads labels at run time.
BB-084 | Deployment & DevOps | Validate database migrations before release | Critical | Passed | DevOps |  | migration-ledger-gate (required); docs/ops/EXPAND_CONTRACT.md; migration-rehearsal.yml |  | Yes
BB-085 | Deployment & DevOps | Configure Docker images and production services | High | In Progress | DevOps |  | docker-compose.prod.yml (app role, pinned web image digest); guard_compose_rls | HO-3 | No | Not deployed to a host.; 2026-10-25 (WP, LLM plan): Kit + preflight ready; Docker-bypasses-ufw check added. Left: deploy on a host.
BB-086 | Deployment & DevOps | Implement deployment rollback | Critical | In Progress | DevOps |  | deploy-staging.yml rollback; docs/ops/FORWARD_FIX.md; RECREATE_FROM_SHA.md | SR1-09 | Yes | Live rollback drill not done.
BB-087 | Deployment & DevOps | Configure domain, DNS and SSL certificates | High | Blocked | DevOps |  | Cloudflare Tunnel compose overlay (db0d317); docs/ops/CDN.md | HO-2 | No | Hosting provider/domain not chosen.; 2026-10-25 (WP, LLM plan): Preflight checks TLS validity, HSTS and HTTP->HTTPS redirect. Left: register domain and DNS.
BB-088 | Deployment & DevOps | Remove development-only settings from production | Critical | Passed | DevOps |  | Production boot refusals; tests/errors/test_freeze_gate_contracts.py |  | Yes | Re-check on the host at first deploy.
BB-089 | Deployment & DevOps | Document deployment and recovery procedures | High | In Progress | DevOps |  | docs/ops/HOSTED_STAGING.md, RELEASE_CHECKLIST.md, RECREATE_FROM_SHA.md, DB_FAILOVER.md | HO-3 | No | Not yet exercised on a host.; 2026-10-25 (WP, LLM plan): First-boot-in-60-minutes runbook added to HOSTED_STAGING.md; drills README. Left: exercise on a host.
BB-090 | Monitoring, Backup & Reliability | Configure application error tracking | High | In Progress | Operations |  | Sentry wiring for API, worker and browser; self-hosted GlitchTip (docker-compose.glitchtip.yml, docs/ops/GLITCHTIP.md); /api/v1/client-errors/ relay; /admin/ops/errors/; test_error_tracker.py, test_client_error_tunnel.py | HO-4 | No | No Sentry project/DSN.; 2026-10-23 ops pass: Free self-hosted GlitchTip replaces a paid Sentry. Live on local staging: API test event and a real browser error captured, Support ID search and ticket links work, alert email + phone push sent. Hosted run pending.; 2026-10-25: self-hosted GlitchTip integrated and tested on local staging (docs/ops/GLITCHTIP.md) - replaces the Sentry need; left: run it on the host and set the DSNs.
BB-091 | Monitoring, Backup & Reliability | Implement structured logging | High | Passed | Operations |  | JSON task logs with request_id; Support ID end to end |  | No
BB-092 | Monitoring, Backup & Reliability | Monitor uptime, API errors and database health | Critical | In Progress | Operations |  | /metrics (multiprocess); health + ready probes; GlitchTip uptime monitors on /api/v1/health/ and ?ready=1; check_error_tracker_task watcher | HO-4; SR1-06 | Yes | No external uptime probe or metrics service.; 2026-10-23 ops pass: Uptime monitors green on local staging with down/up alerts to email + ntfy push (fixed GlitchTip 6 private-IP flag). In-stack only: an external probe of the public edge and a status page are still pending.; 2026-10-24: public status page done (BB-128, /status/). Left: an external probe of the public edge and a metrics service on the host.; 2026-10-25 (WP, LLM plan): Fixed: Prometheus could not scrape the API at all (/api/v1/metrics/ 500 from a root-owned multiprocess dir); health probe now answers 503 when the DB is down. Left: external uptime probe on the host.
BB-093 | Monitoring, Backup & Reliability | Configure alerts for critical failures | Critical | In Progress | Operations |  | 13+ alert rules with runbook sections (test_alert_rules.py); docs/ops/ALERTS.md; GlitchTip alert rules (new error, API down) to email + ntfy; OPS_NTFY_URL for Bizboard ops pages | HO-4; HO-5 | Yes | No receiver/on-call phone; no test page received.; 2026-10-23 review: Fixed: SMS cap-80% page missed the first crossing after a restart; pumping alert no longer fires on the kill switch.; 2026-10-23 ops pass: Alerts now reach a person on local staging: email to the founder and ntfy phone push (delivery to the topic confirmed). Prometheus rules still need test-fires on the host.; 2026-10-25: receiver chosen (D-02: founder email + ntfy phone push); left: a backup on-call person and a live alert test on the host.; 2026-10-25 (WP, LLM plan): Alert paths verified end to end locally (GlitchTip monitors 20-50 s, Prometheus worker 5 min / beat 10 min, ops relay); Alertmanager overlay + relay accepts Bearer and formats Alertmanager pages. Left: backup on call, host test.
BB-094 | Monitoring, Backup & Reliability | Monitor disk space, CPU and memory | High | Blocked | Operations |  | Alert rules ready | HO-4 | No | Needs host metrics.; 2026-10-23 ops pass: No change: needs host metrics.
BB-095 | Monitoring, Backup & Reliability | Schedule automated database backups | Critical | In Progress | Operations |  | Scheduled backups beat task (test_settings_scheduled_backup.py); backup refuses RLS-empty dump; BACKUP_ALERT.md; glitchtip-backup service (scripts/backup.sh BACKUP_KIND=glitchtip); test_backup_scripts.py | HO-12 | Yes | Off-host encrypted backups and PITR need the host.; 2026-10-23 ops pass: Error-tracker database added to the nightly backup with the same encryption/off-site/retention rules; tested on local staging (163 tables).
BB-096 | Monitoring, Backup & Reliability | Define backup retention policies | High | In Progress | Operations |  | docs/ops/BCP.md; DR_CADENCE.md; docs/roadmap/SIGNOFF_PACK_2026-10-23.md B-8 | HO-19 | No | Retention not signed.; 2026-10-24 A/B pass: Proposal: 30 daily + 12 monthly encrypted off-host, PITR 7 days. Awaiting founder signature.
BB-097 | Monitoring, Backup & Reliability | Perform and document an actual backup restoration test | Critical | In Progress | Operations |  | scripts/restore_drill.sh PASS 2026-10-22 (147 s, books check as app role); backup-restore-drill.yml | HO-12 | Yes | Drill against real off-host backups pending.
BB-098 | Monitoring, Backup & Reliability | Define recovery time and recovery point objectives | High | In Progress | Operations |  | docs/ops/SLO.md; BCP.md (draft); docs/roadmap/SIGNOFF_PACK_2026-10-23.md B-9 | HO-19 | No | RPO/RTO not signed.; 2026-10-24 A/B pass: Proposal: RPO 15 min, RTO 4 h. Awaiting founder signature.
BB-099 | Monitoring, Backup & Reliability | Test disaster recovery and incident response | Critical | In Progress | Operations |  | docs/ops/DB_FAILOVER.md, INCIDENT_RESPONSE.md (runbooks only); docs/ops/TABLETOP_EXERCISES.md (4 scenarios); DR_CADENCE.md rows | SR2-10 | Yes | No DR/failover drill or incident tabletop held.; 2026-10-23 ops pass: Tabletop pack written; the session itself is not held yet. Failover drill needs hosted Postgres.; 2026-10-25 (WP, LLM plan): Technical game day run on local staging with real alerts (docs/ops/DRILLS/2026-10-25_LOCAL_GAME_DAY.md): db/redis/beat/worker down, error, stale backup, rollback all detected/recovered; found and fixed /api/v1/metrics/ permanent 500 and health probe 500 when DB down. Tabletop run pack ready. Left: founder tabletop, failover on hosted Postgres.
BB-100 | UI/UX & Customer Onboarding | Review every screen and user journey | High | In Progress | UX |  | docs/reviews/BB100_JOURNEY_WALKTHROUGH_2026-10-24.md: 11 journeys walked in a real browser on local staging (sale, payment, return, purchase with new supplier, quotation convert, reports, settings, help/support, Hindi, phone, sales-staff login); route sweep 138 pages desktop + phone, all flagged pages fixed; earlier surface crawl and docs/UX_ACTION_ITEMS.md; second pass 2026-10-24: phone focus/shortcut hints, staff 403 calls, purchase banner, /help render time fixed (findings F5-F9) | QOS-0097 | No | QOS-0097; 2026-10-24: findings F1, F3, F5-F10 fixed and verified on local staging; open: F2 (GSTR-1 bills of supply, CA), F4 (Hindi FAQ), human pass on real devices.; 2026-10-24: F4 Hindi FAQ draft wired in; F2 options note for the CA written.; 2026-10-24: route sweep after all fixes, desktop and phone, 138 pages each, 0 flagged.; 2026-10-25: /help now shows its first text ~0.5 s after other pages (was 3.6 s originally).
BB-101 | UI/UX & Customer Onboarding | Validate navigation, forms, buttons and permissions | High | Passed | UX |  | Staff login: all 29 menu links open, none lands on limited access; blocked pages show the limited-access notice (BB100_JOURNEY_WALKTHROUGH_2026-10-24.md). Scroll regions keyboard-focusable (a11y/scrollRegions.guard.test.ts); phone sweep 138 pages, no sideways page scroll on 12 key pages; role matrix tests; team list for assignee pickers: GET /company/members/ (id, name, role) for any active member, /company/users/ stays owner-only (test_team_members.py, LeadsPage.test.tsx) | QOS-0096 | No | 2026-10-24: closed. Left for the human pass: real touch devices and screen readers (BB-100).; 2026-10-24 F10: managers and staff could reassign leads/tickets but saw an empty picker; fixed and verified live with the sales-staff login.
BB-102 | UI/UX & Customer Onboarding | Test responsive layouts and usability | Medium | In Progress | UX |  | Phone-width crawl | QOS-0132 | No | Real-device pass open.; 2026-10-24: phones no longer jump past the first fields on new invoice/purchase; shortcut hints hidden on touch devices. Real-device pass still open.; 2026-10-24: phone sweep 138 pages, 0 flagged.
BB-103 | UI/UX & Customer Onboarding | Improve error messages and validation feedback | High | Passed | UX |  | Every data page has loading/empty/error states (pageStates.guard.test.ts); switched-off pages show a notice, not a raw error (FeatureOffNotice, navigation/switchedOff.test.ts); Hindi strings checked for English leftovers (i18n/hiNotEnglish.test.ts); stable error codes translated en/hi | QOS-0098 | No | 2026-10-24: closed. FAQ answer text is still English in Hindi (finding F4, human Hindi review).; 2026-10-24: FAQ answers now show in Hindi (machine draft, 284 entries, marked unreviewed on the page); a native speaker must review.; 2026-10-25: Hindi FAQ uses the app's own Hindi for 74 on-screen labels and one word for "allocation"; native review still needed.
BB-104 | UI/UX & Customer Onboarding | Provide empty states and contextual help | Medium | Passed | UX |  | Grid loading/empty/error states; Help menu, What's new; web/src/pages/pageStates.guard.test.ts; QOS-0098 verified (jsxLiteralRatchet, mfgGridStates, LeadFormPage tests) | QOS-0098 | No | 2026-10-24 A/B pass: All 173 data pages handle loading/error/empty states (one deliberate fallback documented); guard keeps it so.
BB-105 | UI/UX & Customer Onboarding | Simplify company setup and GST configuration | High | In Progress | UX |  | Setup wizard; onboarding checklist (test_onboarding_gr2.py) | SR2-02 | No | Unaided setup by a real business not observed.
BB-106 | UI/UX & Customer Onboarding | Enable customers to create their first invoice independently | Critical | In Progress | UX |  | Onboarding checklist tracks time to first invoice; saas_metrics | QOS-0029 | Yes | Needs real users doing it unaided.
BB-107 | UI/UX & Customer Onboarding | Validate first purchase and inventory setup workflows | Critical | In Progress | UX |  | Golden e2e purchase/inventory journeys | QOS-0029 | Yes | Needs real users.
BB-108 | UI/UX & Customer Onboarding | Provide onboarding guides and FAQs | Medium | Passed | Support |  | docs/help/ (IMPORT_FROM_TALLY, LEGACY_IMPORT, DATA_EXPORT_FORMAT, LIMITATIONS, WHATS_NEW); In-app Help centre FAQ (faqContent.tsx, 250+ answers) + 16 account/subscription answers; faqAccount.test.ts; docs/pilot/FAQS.md |  | No | No FAQ set yet.; 2026-10-24 A/B pass: The "no FAQ" note was stale: 236 answers existed. Added plan change, Autopay, failed payment, Bizboard GST invoices, TDS claim, cancel, data export, Busy/Vyapar/Marg import, two-step, devices, Google, ownership, owner recovery, support, support access, checklist.
BB-109 | UI/UX & Customer Onboarding | Test with actual business users without developer assistance | Critical | Not Started | Product |  | docs/pilot/RECRUITMENT.md §5-6 | HO-15; HO-16; QOS-0029; QOS-0030 | Yes | No beta businesses signed yet.; 2026-10-23 ops pass: Recruitment tracker and import + parallel-month procedure ready; no pilots signed.
BB-110 | Integrations | Validate GST portal integration | High | Accepted Risk | Integration |  | GSP_LIVE_ENABLED off; /limits key 'filing' |  | No | Not in this release.
BB-111 | Integrations | Validate payment gateway integration | Critical | Blocked | Integration |  | Razorpay sandbox; webhook tests | HO-18; QOS-0031 | Yes | Live account and live recon pending.; 2026-10-23 ops pass: Sandbox runs skipped: no Razorpay test keys yet.
BB-112 | Integrations | Validate SMS/OTP provider integration | High | Blocked | Integration |  | MSG91 via DLT template registry; SMS guard (test_sms_guard.py, test_message_templates.py) | HO-6 | No | TRAI DLT entity/templates pending.; 2026-10-23 review: Phone numbers normalised once before the SMS guard, DLT check and provider.
BB-113 | Integrations | Validate WhatsApp Cloud API integration where included | Medium | Accepted Risk | Integration |  | ENABLE_WHATSAPP_CLOUD off; /limits key 'whatsapp' | HO-6 | No | Share link only; template approval needed before turning on.
BB-114 | Integrations | Validate Tally integration where included | Medium | In Progress | Integration |  | Tally CSV/XLSX/XML import; admin grant per pilot (test_tally_xml_import.py) |  | No | Needs real pilot Tally exports; no live sync (documented).
BB-115 | Integrations | Test API authentication and authorization | Critical | Passed | Security |  | JWT cookie auth; X-Company-Id rule; route matrix isolation tests |  | Yes | Pentest will re-check (HO-10).
BB-116 | Integrations | Test timeout, retry and failure handling | High | Passed | Engineering |  | Circuit breakers, timeouts, DLQ + replay; docs/ops/INTEGRATIONS.md |  | No
BB-117 | Integrations | Prevent duplicate requests and webhook processing | Critical | Passed | Engineering |  | Idempotency keys; webhook dedupe; test_w0_webhook_holding.py |  | Yes
BB-118 | Integrations | Monitor integrations and rotate credentials securely | High | In Progress | Operations |  | rotate_encrypted_fields; docs/ops/SECRET_ROTATION.md; integration alerts | HO-13 | No | Rotation drill on the host pending.
BB-119 | Integrations | Document integration limitations and support procedures | Medium | Passed | Support |  | docs/help/LIMITATIONS.md; docs/ops/INTEGRATIONS.md; VENDOR_SLA.md |  | No
BB-120 | Legal & Business Operations | Publish terms of service | Critical | Blocked | Legal |  | Acceptance recording built | HO-9 | Yes | Counsel to write.; 2026-10-24 (D-07): first drafts for counsel in docs/legal/drafts/ (terms, privacy policy, DPA), with sub-processors and open points listed. Counsel must rewrite and approve.
BB-121 | Legal & Business Operations | Publish privacy policy | Critical | Blocked | Legal |  | Acceptance recording built | HO-9 | Yes | Counsel to write.; 2026-10-24 (D-07): first drafts for counsel in docs/legal/drafts/ (terms, privacy policy, DPA), with sub-processors and open points listed. Counsel must rewrite and approve.
BB-122 | Legal & Business Operations | Define cancellation and refund policies | High | In Progress | Legal |  | docs/ops/REFUND_CANCELLATION.md (draft); BL1 refund/credit flow; test_tds_claims_trial_guard.py (review-fix tests); docs/roadmap/SIGNOFF_PACK_2026-10-23.md B-4; docs/ops/REFUND_CANCELLATION.md (updated) | HO-9 | No | Counsel to approve.; 2026-10-23 review: Fixed: TDS refunds could be paid twice (concurrency, rollback after refund); idempotency keys added.; 2026-10-24 A/B pass: Policy proposal drafted; refund doc corrected (proration exists). Awaiting founder decision, then counsel wording.
BB-123 | Legal & Business Operations | Review applicable Indian privacy and data protection obligations | Critical | In Progress | Legal |  | DPDP posture; DATA_CATEGORIES.md; SUBPROCESSORS.md; DPDP request register (DPDP_REQUESTS.md); PRODUCT_BEHAVIORS_FOR_COUNSEL.md | HO-9 | Yes | Counsel review and DPIA decision pending.; 2026-10-25 (WP, LLM plan): DPIA first draft written (docs/legal/drafts/DPIA_DRAFT.md): roles, data, flows, 13 risks with controls, rights, breach; 7 questions for counsel. Left: counsel decides if mandatory and approves.
BB-124 | Legal & Business Operations | Review GST, taxation and invoicing obligations for Bizboard itself | Critical | Blocked | Legal |  | Platform GST invoices built (BL2) | X-01; HO-7 | Yes | Bizboard's own GST registration, books and TDS need the CA.
BB-125 | Legal & Business Operations | Define customer support channels and escalation process | High | In Progress | Support |  | In-app support tickets with SLA timers (PO3); SUPPORT_MACROS.md; TICKET_TAXONOMY.md; test_saas_review_fixes.py | SR2-06 | No | No staffed channel yet.; 2026-10-23 review: Fixed: staff could not reply in the ticket admin (crash on save); lapsed tenants can raise tickets; closing a ticket ends support access at once.
BB-126 | Legal & Business Operations | Establish issue severity and response targets | High | In Progress | Support |  | P0-P3 severity with SLA due dates built; docs/roadmap/SIGNOFF_PACK_2026-10-23.md B-10 | SR2-06 | No | Targets not signed.; 2026-10-24 A/B pass: Severity targets proposed (P0 2 h ... P3 2 business days). Awaiting founder signature.
BB-127 | Legal & Business Operations | Document customer data migration and offboarding | High | In Progress | Operations |  | docs/ops/CUTOVER.md; readable export (DL1); erasure playbook |  | No | Not exercised with a real customer.; 2026-10-23 review: Owners can now see and cancel a pending ownership transfer or staff recovery on Settings > Users.
BB-128 | Legal & Business Operations | Define incident communication and notification procedures | High | Passed | Operations |  | docs/ops/STATUS_COMMS.md (procedures + status page section); public status page from GlitchTip uptime monitors served by nginx at /status/ (no cookies, strict CSP), auto-created by deploy/glitchtip/bootstrap.py, test in test_error_tracker.py; verified on local staging 2026-10-24 (both monitors up); in-app announcement banners (CM3); breach-notice fields | SR1-06 | No | 2026-10-24: closed. Goes public when the edge is deployed on the real domain.
BB-129 | Legal & Business Operations | Review applicable contractual obligations with a qualified professional | High | In Progress | Legal |  |  | HO-9 | No | DPA and vendor contracts not reviewed by counsel.; 2026-10-24 (D-07): first drafts for counsel in docs/legal/drafts/ (terms, privacy policy, DPA), with sub-processors and open points listed. Counsel must rewrite and approve.; 2026-10-24: DPA first draft ready for counsel (docs/legal/drafts/DATA_PROCESSING_AGREEMENT_DRAFT.md); counsel review still needed.; 2026-10-25 (WP, LLM plan): Vendor contract checklist drafted (docs/legal/drafts/VENDOR_CONTRACT_CHECKLIST.md): 14 checks per launch vendor and our DPA promises mapped to vendor terms; SUBPROCESSORS.md now lists the AI provider, Google, Cloudflare, Telegram, identity check, AA, host. Left: vendor terms + counsel.
BB-130 | Sales, Marketing & Go-to-Market | Finalize positioning and value proposition | High | In Progress | Marketing |  | docs/COMPETITIVE_ANALYSIS_BIZBOARD.md; GROWTH_OS_DECISIONS_2026-09-30.md; docs/roadmap/SIGNOFF_PACK_2026-10-23.md B-11 |  | No | Not finalised.; 2026-10-24 A/B pass: Positioning statement drafted. Awaiting founder signature.
BB-131 | Sales, Marketing & Go-to-Market | Complete competitor analysis | Medium | Passed | Marketing |  | docs/COMPETITIVE_ANALYSIS_BIZBOARD.md (2026-09-22) |  | No | Refresh before launch.
BB-132 | Sales, Marketing & Go-to-Market | Define customer segments and acquisition channels | High | In Progress | Marketing |  | BUSINESS_ARCHETYPES_AND_PERSONAS.md; Growth OS 3 parallel pilots; docs/roadmap/SIGNOFF_PACK_2026-10-23.md B-12 |  | No | 2026-10-24 A/B pass: Segments and channels drafted. Awaiting founder signature.
BB-133 | Sales, Marketing & Go-to-Market | Publish website and pricing page | High | In Progress | Marketing |  | Public /limits page ready to link |  | No | No website or pricing page yet.; 2026-10-25 (D-15): draft site and pricing page in site/ (English + Hindi home, noindex, prices marked draft); not published. Waits on signed prices, domain and approved legal pages.; 2026-10-25: pricing page now lists GST worksheets on every plan (D-16).
BB-134 | Sales, Marketing & Go-to-Market | Prepare product demo and onboarding material | High | Passed | Marketing |  | seed_demo --with-activity (tests/test_seed_demo_activity.py); docs/onboarding/DEMO_SCRIPT.md |  | No | Practice company with demo data deferred (G-04).; 2026-10-24 A/B pass: Demo company with 3 months of invoices, receipts (paid/part/unpaid) and a return; 20-minute demo script with honest answers. In-product practice company (G-04) stays deferred.
BB-135 | Sales, Marketing & Go-to-Market | Define pilot customer acceptance criteria | Critical | In Progress | GTM |  | FULL_SPECTRUM_PERSONA_VALIDATION_PLAN.md; SR2 done-whens (zero unexplained recon, a day without an engineer); docs/roadmap/SIGNOFF_PACK_2026-10-23.md B-13 |  | Yes | Not agreed with pilot customers.; 2026-10-24 A/B pass: Six acceptance criteria drafted. Awaiting founder signature and pilot agreement.
BB-136 | Sales, Marketing & Go-to-Market | Establish customer feedback collection | High | Passed | GTM |  | docs/ops/FEEDBACK_TRIAGE.md; in-app support tickets; NPS prompt + CSAT on resolved support requests behind ENABLE_SATISFACTION_SURVEY (off by default); staff read answers and NPS in Django admin; test_satisfaction_survey.py, NpsPrompt.test.tsx; verified live on local staging |  | No | NPS/CSAT deferred (P-04).; 2026-10-24 (D-08): survey built, P-04 deferral lifted. Left: turn it on per company once pilots start.; 2026-10-24: closed - in-app NPS and support CSAT built and verified, answers in Django admin, triage in FEEDBACK_TRIAGE.md. Switch it on per company when pilots start.
BB-137 | Sales, Marketing & Go-to-Market | Define trial-to-paid conversion process | High | In Progress | GTM |  | Trial expiry write-block; checkout; trial-to-paid metric; docs/roadmap/SIGNOFF_PACK_2026-10-23.md B-5 | HO-18 | No | Process not signed.; 2026-10-24 A/B pass: Trial-to-paid process drafted (no automatic welcome email yet; founder sends). Awaiting founder signature.
BB-138 | Sales, Marketing & Go-to-Market | Track activation, retention, churn and support load | High | In Progress | GTM |  | Tenant health score + /admin/ops/saas-metrics/ (activation, trial-to-paid, churn, NRR, tickets/100) |  | No | Tooling built; no real tenants yet.; 2026-10-23 review: Fixed: metrics counted sandbox/erased companies; churn/NRR hidden for a month still running; per-company queries removed.
BB-139 | Sales, Marketing & Go-to-Market | Establish customer referral and feedback mechanism | Medium | Passed | GTM |  |  |  | No | Referral programme planned after launch (G-03).; 2026-10-23 ops pass: Deferred to after launch by plan (G-03); not a launch blocker.; 2026-10-24: feedback half done (NPS/CSAT, BB-136); referral programme still deferred to after launch (G-03).; 2026-10-25 (WP, LLM plan): Bizboard referral programme built behind ENABLE_SAAS_REFERRALS (off, D-19): link + WhatsApp share in Settings > Billing, ?ref= on password and Google sign-up, daily qualification on paid activation, same-business and daily-cap guards, reward recorded only and settled by staff in admin (docs/ops/REFERRALS.md). RLS migration core 0074; test_saas_referrals.py 11 + 2 Postgres app-role tests pass. Feedback half done earlier (BB-136).
BB-140 | Final Launch Readiness | Resolve all critical business logic defects | Critical | In Progress | Launch |  | Review programmes fixed many critical defects (see handover section 4 and plan records); docs/roadmap/SAAS_FULL_PRODUCT_IMPLEMENTATION_PLAN_2026-10-22.md section 10 | QOS-0004; QOS-0097 | Yes | CA sign-offs and real-user runs still open.; 2026-10-23 review: Deep review of the SaaS Phase 1+2 code: about 130 candidates, real ones fixed with tests.; 2026-10-24: quote/order GST total could differ from the invoice (BB-100 F1) - fixed for quotations, sales and purchase orders.
BB-141 | Final Launch Readiness | Pass all critical end-to-end test scenarios | Critical | In Progress | Launch |  | Golden e2e live pass; strict invariant lane | SR0-01 | Yes | Not on hosted staging; tree partly uncommitted.; 2026-10-25 (WP, LLM plan): CI half run locally (see BB-017). Left: commit + hosted staging.
BB-142 | Final Launch Readiness | Pass financial and inventory reconciliation tests | Critical | In Progress | Launch |  | GL parity invariants; restore drill sweep clean; docs/pilot/RECRUITMENT.md §6 (compare_trial_balance steps) | HO-15 | Yes | Parallel month with real pilots (compare_trial_balance) pending.; 2026-10-23 ops pass: Parallel-month procedure written; needs real pilots.
BB-143 | Final Launch Readiness | Pass cross-tenant security tests | Critical | In Progress | Launch |  | Tenancy + RLS suites pass on Postgres app role; test_saas_review_fixes_postgres.py | SR1-02; HO-10 | Yes | Hosted run and pentest pending.; 2026-10-23 review: Postgres-only RLS regressions from the review added.; 2026-10-24: Postgres-only suites (row-level security, concurrency, tenancy) re-run on a fresh local Postgres: 543 passed, 1 skipped. Still to run on the hosted database.; 2026-10-25 (WP, LLM plan): Same as BB-029 (local probe clean). Left: hosted run and pentest.
BB-144 | Final Launch Readiness | Resolve all critical security vulnerabilities | Critical | Blocked | Launch |  | CodeQL, Trivy, dependabot clean in CI | HO-10 | Yes | Independent pentest not done.; 2026-10-25 (WP, LLM plan): Local scan findings fixed (headers, JSON API errors, 3 high npm advisories: zod 4.6.7, follow-redirects 1.16.1, fast-uri 3.1.9; pip-audit clean). Left: pentest findings and their fixes.
BB-145 | Final Launch Readiness | Verify successful backup restoration | Critical | In Progress | Launch |  | Local restore drill PASS 2026-10-22 | HO-12 | Yes | Hosted off-host drill pending.
BB-146 | Final Launch Readiness | Verify production monitoring and alerts | Critical | In Progress | Launch |  | Alert rules + runbooks built; GlitchTip error tracking + alerts live on local staging; on-call primary named | HO-4; HO-5 | Yes | No Sentry, metrics service or on-call.; 2026-10-23 ops pass: Error tracking, alerts and an on-call person now exist (local staging). Hosted verification and metrics service pending.
BB-147 | Final Launch Readiness | Verify payment and subscription workflows | Critical | Blocked | Launch |  | Billing flows tested in repo; 152 billing/gateway tests pass (mocked gateway) | HO-18 | Yes | Razorpay sandbox runs and live account pending.; 2026-10-23 ops pass: Sandbox runs skipped: no Razorpay test keys yet.
BB-148 | Final Launch Readiness | Obtain pilot customer acceptance against agreed criteria | High | Not Started | Launch |  | docs/pilot/RECRUITMENT.md §5-6 | HO-15 | No | No pilots signed.; 2026-10-23 ops pass: Recruitment tracker and import + parallel-month procedure ready; no pilots signed.
BB-149 | Final Launch Readiness | Confirm support, incident response and rollback readiness | Critical | In Progress | Launch |  | Runbooks: INCIDENT_RESPONSE, HYPERCARE, ONCALL_ROSTER (template), rollback workflow; ONCALL_ROSTER.md (primary named) | HO-5; SR1-09 | Yes | On-call not named; rollback drill not done.; 2026-10-23 ops pass: On-call primary named; no backup. Rollback drill still not done.; 2026-10-25 (WP, LLM plan): Rollback drill on local staging: 142 s back, 133 s forward; alerts verified. Left: on-call backup, host drill.
BB-150 | Final Launch Readiness | Document launch approval and known-risk register | High | In Progress | Launch |  | docs/ops/RISK_REGISTER.md; SAAS_READINESS_HANDOVER_2026-10-22.md; docs/ops/RISK_REGISTER.md (refreshed, 18 risks + 12-gate launch approval sheet) |  | No | Launch approval not given.; 2026-10-24 A/B pass: Register refreshed and launch approval sheet added. Awaiting founder decisions per risk and signature.

## Read Me
HOW TO USE THIS WORKBOOK
Topic | Guidance
Purpose | Track Bizboard's readiness to operate as a secure, reliable SaaS product.
Update status | Use the dropdown in the Status column: Not Started, In Progress, Blocked, Passed, Accepted Risk.
Evidence | For every Passed item, add a test ID, deployment record, screenshot, review note or other verifiable evidence.
Critical items | Critical items are proposed release blockers. Do not mark them Passed without verification.
Ownership | Assign an accountable owner for each item. One person may own multiple items.
Dates | Fill Target Date only after agreeing a realistic plan.
Risks | Use Defect / Risk ID and Notes to link the item to the bug tracker or risk register.
Launch decision | Use the checklist as a gate, not just a completion percentage. A high percentage does not override a failed critical security or data-integrity item.
Scope note | Some integrations and compliance tasks are conditional on the features Bizboard actually offers and the applicable rules.